## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
COP4331 Small Project
Contact Manager |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-08-30 |  |  |  |  | August | [6 empty] | September | [27 empty] | October
Scrolling Increment: | 1 | time axis 2021-08-31 to 2021-10-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-08-31 to 2021-10-25
Documentation
Gantt Chart | Low Risk | Matias | 25% | 2021-08-30 | 1
Database | Low Risk | Calvin, Matias | 100% | 2021-08-30 | 1
API | Low Risk |  | 0% | 2021-08-30 | 10
Task 4 | Milestone |  |  | 2021-09-19 | 1 | bar: 2021-09-19
Task 5 | Med Risk |  | 10% | 2021-09-05 | 6
Database
Task 1 | High Risk |  | 60% | 2021-09-05 | 13
Task 2 | On Track |  | 50% | 2021-09-07 | 9
Task 3 | Low Risk |  | 33% | 2021-09-12 | 11
Task 4 | Milestone |  |  | 2021-09-14 | 1 | bar: 2021-09-14
Task 5 |  |  |  | 2021-09-15 | 24
API
Task 1 | On Track |  |  | 2021-09-14 | 4
Task 2 | Med Risk |  |  | 2021-09-17 | 14
Task 3 | On Track |  |  | 2021-10-02 | 6
Task 4 | Goal |  |  | 2021-10-06 | 3 | 2021-10-06: 2; 2021-10-07: 2; 2021-10-08: 2
Task 5 | Low Risk |  |  | 2021-09-05 | 19
Frontend
Task 1 |  |  |  | 2021-10-09 | 15
Task 2 |  |  |  | 2021-10-23 | 5
Task 3 | Milestone |  |  | 2021-12-04 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-09-21 |  |  |  |  | September | [13 empty] | October | [27 empty] | November
Scrolling Increment: | 1 | time axis 2021-09-22 to 2021-11-16
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-09-21 | 3 | W: 2; T: 2
Task 2 | Milestone |  |  | 2021-09-26 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2021-09-18 | 10
Task 4 | Milestone |  |  | 2021-10-11 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2021-09-27 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-09-27 | 13
Task 2 | On Track |  | 50% | 2021-09-29 | 9
Task 3 | Low Risk |  | 33% | 2021-10-04 | 11
Task 4 | Milestone |  |  | 2021-10-06 | 1 | bar: W
Task 5 |  |  |  | 2021-10-07 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-10-06 | 4
Task 2 | Med Risk |  |  | 2021-10-09 | 14
Task 3 | On Track |  |  | 2021-10-24 | 6
Task 4 | Goal |  |  | 2021-10-28 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2021-09-27 | 19
TITLE 4
Task 1 |  |  |  | 2021-10-31 | 15
Task 2 |  |  |  | 2021-11-14 | 5
Task 3 | Milestone |  |  | 2021-12-26 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
COP4331 Small Project
Small Project Gantt Chart |  |  |  |  | Legend: | On Track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Contact Manager
Project Start Date: | 2021-08-25 |  |  |  |  | August | [6 empty] | September | [34 empty] | October
Scrolling Increment: | 0 | time axis 2021-08-25 to 2021-10-19
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-08-25 to 2021-10-19
Documentation
Create Gantt chart | On Track | Matias | 50% | 2021-08-30 | 2
Powerpoint | High Risk | Matias | 0% | 2021-09-09 | 18
UML | Low Risk | Jon | 100% | 2021-09-04 | 3
ERD | Low Risk | Calvin | 100% | 2021-09-07 | 3
Database
DIgitalOcean Server Setup | On Track | Matias | 100% | 2021-08-26 | 2
Database creation | Low Risk | Calvin, Matias | 100% | 2021-08-30 | 3
Populate database | Med Risk | Calvin | 50% | 2021-08-31 | 6
API
Login Endpoint | Med Risk | Jon, Tanner | 100% | 2021-09-03 | 7
Add Endpoint | Med Risk | Jon | 100% | 2021-09-07 | 7
Delete Endpoint | High Risk | Tanner | 100% | 2021-09-10 | 10
Search Endpoint | High Risk | Jon, Tanner | 100% | 2021-09-04 | 14
Edit Endpoint | Low Risk | Jon | 100% | 2021-09-06 | 7
Swaggerhub Testing | High Risk | Tanner, Jon | 25% | 2021-09-20 | 7
Frontend
Purchase Domain | Goal | Matias | 100% | 2021-09-01 | 1 | 2021-09-01: 2
Contact Page | Med Risk | Alex, Tanner | 60% | 2021-09-06 | 18
Login/Signup Page | Low Risk | Alex, Tanner | 70% | 2021-09-01 | 14
To add more data, Insert new rows ABOVE this one